## Sheet1
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | Yes | Yes | High | In progress | 20 | Yes
Database Design | No | No | High | In progress | 5 | Yes
User Registration | Yes | Yes | High | In progress | 3 | Yes
User Login | Yes | Yes | High | Complete | 3 | Yes
Role-Based Access Controls | Yes | No | High | In progress | 4 | Yes
Sprint 2 | Yes | No | Medium | Not Started | 15 | Yes
Brand Creation Features | Yes | No | High | Not started | 5 | Yes
Sprint 3 | Yes | No | Medium | Not Started | 4 | Yes
E-commerce Integration | Yes | No | High | Not Started | 3 | Yes
Networking Features | Yes | No | Medium | Not Started | 15 | Yes
Marketing Tools | Yes | No | Medium | Not started | 4 | Yes
Event Management Features | Yes | No | Medium | Not Started | 15 | Yes
Sprint 4 | Yes | No | Medium | Nor Started | 15 | No
Progress Tracking | Yes | No | High | Not Started | 3 | No
Security Enhancements | Yes | No | High | Not Started | 3 | No
Deployment | Yes | No | High | Not Started | 3 | No